## Slide 1: Project Charter: CASIC SCORING PROJECT 1/2
Case for change / Problem Statement
CASIC lacks a data driven approach to review submissions. Underwriters are only able to review 9,000 of the 60,000 submissions received annually. Underwriters choose submissions to review based on their familiarity with the brokers and/or the insured, or their intuition. When selecting a submission to review, the underwriters do not know its likelihood to be profitable. Therefore, the CASIC could be missing out on winnable deals.
Business Case
Underwriters are to receive submissions sorted in the descending order of their score (likelihood to win) in their inbox post project completion, enabling to make data-driven decisions. As a result of this improved submission prioritization process, profit margins are expected to increase by upto 20% by the second year of model use. A margin increase of only 8% helps the submission scoring project achieve the committed NPV of $500,000 in this time frame. The project is expected to recover the investment of $283,000 within 1.67 years from the project start date and the internal rate of return of the project is 167%.
In Scope | Out of Scope
Building a model to score submissions | Training the IT team
Model documentation and underwriter training | Working on model refresh
Consulting with CASIC’s IT team to enable model integration in workflow | Actual model integration
Constraint Matrix (Priority Matrix) |  |  | 
 | MOST | SOME | LEAST
SCOPE | x |  | 
TIME |  | x | 
COST |  |  | x
Top Risks (max. 5)
Historic data based on the underwriter’s bias in previous selections might affect the result. The model may be complicated and difficult to integrate in CASIC’s workflow. Employees fail to learn the system. Conducting training sessions as per underwriters' varying schedule might not be feasible for our team.
Objectives / Goal statements
Having objective selection criteria for evaluating submissions. Building a scoring model that predicts the likelihood of a submission to be profitable with acceptable level of accuracy. Providing consultation to CASIC’s IT team, helping them integrate the ML model in company’s native software/ systems Compiling model documentation and training underwriters on using the tool Completing the project by October 2023 within the allotted budget of $283,000.
Assumptions
Historical data is applicable and clean. Construction of predictive model for such a scenario is possible. The team has full access to the stakeholders for clarification and answers about the project.
10-10-2022

## Slide 2: Project Charter: CASIC SCORING PROJECT 2/2
Incoming Dependency | Outgoing Dependency
Previous data for modeling | N/A
Underwriters’ schedule | 
Consultation access from Allen and Stakeholders | 
Deliverables & Milestones (High Level Milestone Plan) |  |  | 
Project Start Date: 09/30/2022 |  | Project End Date: 10/05/2023 | 
Key Deliverable | Milestone Name (MN) |  | Planned MS Date
Problem and Solution Definition | Fundamental Data |  | 10-10-2022
Initial Predictive Model | Learning Data I |  | 12-20-2022
Final Predictive Model | Learning Data II |  | 02-15-2023
Model Selection and Parameter Setting | Training Data |  | 04-10-2023
Model Deployment Solution | Management Data |  | 05-12-2023
Model Output Monitoring | Retraining Data |  | 07-20-2023
Underwriter Training | Training associates |  | 08-30-2023
Tool incorporation in the CASIC workflow, | Tool integration |  | 10-12-2023
Signoff |  | 
Role | Signature | Date
Sponsor | Allen Nobody / UConn MSBAPM | 
PSB Member | Allen Nobody | 10-10-2022
PSB Member | CIO | 10-10-2022
PSB Member | CUO | 10-10-2022
PSB Member |  | 
PSB Member |  | 
Beneficiary | Underwriters | 
Beneficiary |  | 
Project Organization | 
Sponsor | Allen Nobody
Steering Board Members (PSB) | Allen Nobody, CIO, CUO
Project Manager | Deepthi Pai Manoor
Workstream Leaders | N/A
Team Members | Sumit, Anu, Enoch, Prasanth
Project Costs (USD) |  | 
Total: $283,000 | Internal:$33,000 | External:$250,000
Project Benefits |  | 
NPV: $1,667,000 | IRR: 167% | Break Even: 1.67 years (payback period)
The project has a NPV of $1,667,000 and recovers the investment of $283,000 in about 1 year and 8 months from the project start date. Indirect Benefits: Employee’s technical certification |  |